## Plan
Activities | Resource | Status | Effort (in hrs) | Start Date | End Date | Dependencies/Comments
Data Understanding |  |  |  | 2019-09-17 | 2019-09-23
Hypothesis Building | [5 empty] | 1. Whether or not the virus is present for a given weather, time, seasonal activity, and location ? 2. The distance between with trap and spray? 3. How the weather & humidity affects the virus presence?
Data Cleaning |  |  |  | 2019-09-26 | 2019-10-03 | Weather & Spray = Sonal, Matthew, Amy Test &Train = Vishnu, Manodhar, Jennifer
Exploratory Data Analysis |  |  |  |  | 2019-10-10 | Weather & Spray = Vishnu, Manodhar, Jennifer Test &Train = Sonal, Matthew, Amy
Dataset prepration |  |  |  |  | 2019-10-14
Model Building
Model Validation
Results |  |  |  |  | 2019-10-23

## Meetings
Meetings Date | Discussion Points | Action Items
2019-09-17 |  | Need to look into the combined mosquito species (weather or not)
2019-09-25 | 1. For EDA : univariate to see what type of value are commonly occuring and what are some missing data | Do Data cleaning, any changes put it in the data dictionary in the master branch on Git, Combine the data after data cleaning

## Data Dictionary
Dataset Name | Column Name | Column Description | Data Type | learning
train.csv, test.csv | ID
| Date | join key | dttm
Address
| Species |  |  | Most mosquito is found in August
Block
Street
Trap
AddressNumberAndStreet
Latitude,Longitude
AddressAccuracy
NumMosquitos
WnvPresent
spray.csv | Date,Time | join key | dttm
Latitude,Longitude
weather.csv |  |  |  | Data Cleaning = multiple records and non distinct data, need to change varchar into numeric
Notes
1. We can use the lat & long to predict if the spray is effective
2. Spray data are incomplete (not for the entire time as the weather data)
3. weather data is available for the whole time
4. look at weather data first --> spray data --> then the train
test

## Questions
S.No | Questions | Answer/Comments | Resolved (Y/N)

## Rough (hidden)
Resources | Resolved (Y/N) | Status
Amy | Y | Completed
Jennifer | N | Delayed
Manodhar |  | WIP
Matthew |  | Not yet started
Sonal
Vishnu